## Senzcraft_Task_Allocation
Module | Sub Task | Backend | Backend Dates | Frontend | Frontend Dates
Frontend HTML | Convert Next.js | Pratyush | 2026-05-21 | Pratyush | 2026-05-21 | Done by Sarthak
Backend | Project Repo | Sarthak | 21–22 May | Sarthak | 21–22 May | Done
Client | [5 empty] | Done
| List Clients | Sarthak | 21–22 May | Sarthak | 21–22 May | Done
| Add Client | Sarthak | 2026-05-25 | Sarthak | 2026-05-25 | Done
| Edit Client | Sarthak | 2026-05-25 | Sarthak | 2026-05-25 | Done
| Delete Client | Sarthak | 2026-05-25 | Sarthak | 2026-05-25 | Done
| Client Detail Page | Sarthak | 2026-05-26 | Sarthak | 2026-05-26 | Done
Process
| Step 1 — Customer Details Form | Sarthak | 2026-05-27 | Sarthak | 2026-05-27 | Done
| Step 1 — Create Process API | Sarthak | 2026-05-27 | Sarthak | 2026-05-27
| Step 2 — Process Details Form | Sarthak | 2026-05-28 | Sarthak | 2026-05-28 | Done
| Step 2 — Save Step 2 API | Sarthak | 2026-05-28 | Sarthak | 2026-05-28
| Step 3 — Volumetrics Form + Cost Estimate | Sarthak | 29 May & 1 Jun | Sarthak | 29 May & 1 Jun | Done
| Step 3 — Save Step 3 API | Sarthak | 29 May & 1 Jun | Sarthak | 29 May & 1 Jun
| Step 4 — File Upload UI (PDF/CSV/Excel) | Sarthak | 2–3 Jun | Sarthak | 2–3 Jun | Done
| Step 4 — Azure Blob Storage Setup | Pratyush | 2026-05-22 | Pratyush | 2026-05-22
| Step 4 — Document Parsing Agent (LangGraph) | Pratyush | 25–27 May | Pratyush | 25–27 May
| Step 4 — Activity Extraction AI Agent (GPT-4o) | Pratyush | 28 May–29 May | Pratyush | 28 May–29 May
| Step 4 — Editable Activity Table UI | Sarthak | 3–5 Jun | Sarthak | 3–5 Jun | Done
| Step 5 — GSDA Scoring UI (Sliders + Gauge) | Pratyush | 1–2 Jun | Pratyush | 1–2 Jun
| Step 5 — GSDA AI Hint Agent | Pratyush | 3–4 Jun | Pratyush | 3–4 Jun
| Step 6 — Archetype Generation Agent (LangGraph) | Pratyush | 5&8 Jun | Pratyush | 5&8 Jun
| Step 6 — Archetype Cards UI | Sarthak | 8–9 Jun | Sarthak | 8–9 Jun
Report
| AI Summary Generation | Pratyush | 9-10 Jun | Pratyush | 9-10 Jun
| PDF Export (ReportLab) | Pratyush | 12-11 Jun | Pratyush | 11-12 Jun
| Summary Page UI | Sarthak | 10-11 Jun | Sarthak | 10-11 Jun
| PDF Download Button | Sarthak | 2026-06-12 | Sarthak | 2026-06-12
Dashboard
| Stats Cards (Clients, Assessments, Avg GSDA) | Sarthak | 15-16 Jun | Sarthak | 15-16 Jun
| Process List Table + Filters | Sarthak | 15-16 Jun | Sarthak | 15-16 Jun
User
Management / Roles
Signup
Login
Logout
🟩 Sarthak = Data Scientist ¦ 🟦 Pratyush = AI Engineer ¦ Dates are estimates — adjust as needed